## Project tracker
Project tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2025-02-24 | 2025-04-25 | 210 | 61 | 2025-02-24 | 2025-04-30 | 300 | 66
Project 2 | Category 2 | Employee 4 | 2025-03-20 | 2025-04-20 | 400 | 30 | 2025-03-20 | 2025-04-23 | 390 | 33
Project 3 | Category 1 | Employee 2 | 2025-01-20 | 2025-03-21 | 500 | 61 | 2025-01-20 | 2025-04-03 | 500 | 73
Project 4 | Category 2 | Employee 3 | 2025-01-30 | 2025-02-09 | 250 | 9 | 2025-01-30 | 2025-02-18 | 276 | 18
Project 5 | Category 3 | Employee 2 | 2025-01-30 | 2025-03-11 | 300 | 41 | 2025-01-30 | 2025-03-17 | 310 | 47
Project 6 | Category 4 | Employee 4 | 2025-03-01 | 2025-03-11 | 500 | 10 | 2025-03-01 | 2025-03-16 | 510 | 15
Project 7 | Category 5 | Employee 1 | 2025-03-17 | 2025-04-10 | 750 | 23 | 2025-03-17 | 2025-04-15 | 790 | 28
Project 8 | Category 2 | Employee 1 | 2025-03-22 | 2025-04-30 | 450 | 38 | 2025-03-16 | 2025-04-25 | 430 | 39
Project 9 | Category 4 | Employee 1 | 2025-01-25 | 2025-02-14 | 250 | 19 | 2025-01-30 | 2025-02-09 | 200 | 9
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS